## GB-Cert-Milestones
Six Sigma Green Belt Certification Process | Introduction | DEFINE (part 1 & 2) | DEFINE (part 3) | MEASURE | ANALYSE | IMPROVE | CONTROL
Course Content | Videos | Videos, Handouts, sigmaGuide, Project-Story-Book | Videos, Handouts, sigmaGuide, Project-Story-Book | Videos, Handouts, sigmaGuide, Project-Story-Book | Videos, Handouts, sigmaGuide, Project-Story-Book | Videos, Handouts, sigmaGuide, Project-Story-Book | Videos, Handouts, sigmaGuide, Project-Story-Book
| 1 Certification-Path | 11 sigmaGuide | 16 DEFINE SIPOC | 20 MEASURE Overview | 26 ANALYSE Overview | 32 IMPROVE Overview | 35 CONTROL Overview
| 2 Course Introduction | 12 DEFINE Overview | 17 DEFINE Voice-to-Critical | 21 MEASURE Input-Analysis | 27 ANALYSE Data-Evaluation | 33 IMPROVE Development and Selection of Solutions | 36 CONTROL Data Evaluation
| 3 Six Sigma Introduction: Overview | 13 DEFINE Project-Topic | 18 DEFINE Project-Charter | 22 MEASURE Process-Mapping-Analysis | 28 ANALYSE Processs-Performance | 34 IMPROVE Measures, Risks (FMEA) and Implementation | 37 CONTROL Process-Performance
| 4 Six Sigma Introduction: Improvement Program | 14 DEFINE Project-Definition | 19 DEFINE Stakeholder-Communication | 23 MEASURE C&E-Matrix | 29 ANALYSE Hypotheses-Tests |  | 38 CONTROL Improvement-Verification and Benefits
| 5 Six Sigma Example: Cookie du Chef | 15 Project-Story-Book |  | 24 MEASURE Data-Collection-Plan | 30 ANALYSE Root-Cause-Analysis - Preparation |  | 39 CONTROL Process-Management-Plan
| 6 Six Sigma Introduction: Method DMAIC |  |  | 25 MEASURE Hypotheses | 31 ANALYSE Root-Cause-Analysis - Implementation |  | 40 CONTROL Project-Completion
| 7 Six Sigma Introduction: Method Process-Problem-Solving-Model | [5 empty] | 41 Six Sigma Project-Guideline
| 8 Six Sigma Introduction: Method Problem-Solving-Principles | [5 empty] | Addendum
| 9 Six Sigma Introduction: Method Statistical-Basis | [5 empty] | 42 Lean and Six-Sigma - Roots and Development
| 10 Six Sigma Introduction: Linking Reality Model & Statistics | [5 empty] | 43 Lean vs Six-Sigma - Comparison of Characteristics
Deliverables & Checks | - TUM Lean Six Sigma Yellow Belt Certificate - Exam questions | - Exam questions - sigmaGuide: Related tools - Results edited in Project-Story-Book (D----) | - Exam questions - sigmaGuide: Related tools - Interviews with local litter removal service (VoB) and pedestrians (VoC) - Results edited in Project-Story-Book (D----) | - Exam questions - sigmaGuide: Related tools - Minitab: Worksheet with collected data - Results edited in Project-Story-Book (DM---) | - Exam questions - sigmaGuide: Related tools - Minitab: Data Inspections and Analyses - Results edited in Project-Story-Book (DMA--) | - Exam questions - sigmaGuide: Related tools - Implementation of measures - Results edited in Project-Story-Book (DMAI-) | - Exam questions - sigmaGuide: Related tools - Minitab: - Process-Capability & Control-Charts; - Verification of benefits - Results edited in Project-Story-Book (DMAIC)
Coaching (Business-Projects) |  | - written feedback on the: suitability of the Project-Topic and quality of the Project-Definition | - written feedback - individual online sessions, scheduled when necessary
Coaching (Standard- & Business-Projects) |  |  | - group online sessions: - introduction of a new DMAIC phase, tools and tasks; Q&A´s (weekly) - introduction of participants, presentation and discussion of projects (weekly) (of the total of approx. 40 sessions at least 10 must be attended)
Decision about phase success (Business-Projects) |  | Master Black Belt (TUM) | Master Black Belt (TUM)
Manager of your company as sponsor of your project
Timeline (Example)
Start of Phase | 2020-01-01 | 2020-01-23 | 2020-02-07 | 2020-02-29 | 2020-04-26 | 2020-05-25 | 2020-07-21
Suggested duration (days) | 21 | 14 | 21 | 56 | 28 | 56 | 14
Suggested End of Phase | 2020-01-22 | 2020-02-06 | 2020-02-28 | 2020-04-25 | 2020-05-24 | 2020-07-20 | 2020-08-04
Formulas:
DEFINE (part 1 & 2) = [Introduction]+[Introduction, row below]+1
Introduction = B19+[Introduction, row above]

## GB-Cert-Steps-Introduction
Introduction
Course Content | Videos
Please watch all videos
Deliverables & Checks | We receive many questions to technical or administrative issues, which we have already specified within the course. In this case we will not answer the question but direct you to the source with the answer. This is necessary, to keep the administration of our course lean.
Coaching (Standard- & Business-Projects)
Decision about phase success (Business-Projects)
Timeline (Example)
Start of Phase | 2020-01-01
Suggested duration (days) | 21
Suggested End of Phase | 2020-01-22
link back to milestones

## GB-Cert-Steps-Define_1_2
DEFINE (part 1 & 2)
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, especially Introduction 2, read handouts, apply sigmaGuide, fill Project-Story-Book template
Deliverables & Checks | 1. Please identify a suitable Six Sigma project for your certification. You can do this by: - observing a deviant process and/ its deviant outputs - interview your Manager about deviations in processes and/ or outputs (Voice of Business/ VoB) - interview (internal) customer about deviant inputs they receive from an upstream process (Voice of Customer/ VoC)
2. Assure, that the responsible Manager for the respective process and ist outputs will support you implementing your project and thus take the role as a Sponsor
3. Please add information about your project to these tools in sigmaGuide: - Project-Topic - Process & Output - Problem - Effect - Solution
4. Check the summary of your information in the Project-Definition of sigmaGuide and correct/ adapt prior given answers if necessary
5. Present and discuss the Project-Definition of sigmaGuide with your Manager/ Sponsor and correct/ adapt answers if necessary. Assure, that you still have the support of your Manager as a Sponsor
6. Confirmation Letter of Sponsor for Business-Projects: To confirm that your manager responsibly supports the implementation of the defined project as a Sponsor, please have him or her specify the information in [brackets] for your project: My name is [managers name] from the company [company name]. I am responsible for the process [process name] and its outputs [output name]. I confirm, that [candidates name & eMail address] will implement the Six Sigma project in my area of responsibility and will support [candidate] in the DMAIC phases (DEFINE, MEASURE, ANALYSE, IMPROVE, CONTROL), in the role of a Sponsor. For the Lean Six Sigma Green Belt certificate he/ she will measurable solve: - a Quality-Problem of the output, - an Availability-Problem (reduce cycle time or increase volume) and - a Consumption-Problem (better utilization of inputs and/or resources and/or elimination of waste in the process). I allow [candidate] to conduct interviews with internal customer of (intermediate) outputs, to involve experts of the topic and to conduct at least one workshop a) in the MEASURE phase to analyse the inputs and the process and b) in the transition of the ANALYSIS to the IMPROVE phase to determine the root causes of the problems and to develop solution ideas to eliminate the root causes. At the end of each DMAIC phase, [candidate] will present the most important results of this phase in his/ her Project-Story-Book. Based on these results, I will decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase. The decision about the implementation of solutions in the IMPROVE-Phase is up to me. I note, however, that a project in which no solutions are implemented and which does not lead to measurable improvements cannot be certified. Therefore, I will check the financial and other benefits for plausibility after the approved solutions are implemented. I accept that the application and registration at the TUM School of Management begins with the sending of this eMail, and that the course fee has to be transferred if the Project-Topic and Project-Definition have passed the suitability check.
7. Please: let your manager in the role of your project Sponsor send: - a copy of the specified confirmation text with the - subject: TUM Green-Belt-Certification to:
caroline.hoffmann@tum.de; reiner.hutwelker@sigmaLogic.de
8. Download and fill out the application form for the Green Belt course:
https://www.eec.wi.tum.de/en/certificate-programs/certified-tum-six-sigma-green-belt-program/
and send it with the subject: TUM Green-Belt-Certification to:
caroline.hoffmann@tum.de
9. Prepare your Project-Story-Book (Videos 7-11): - complete all pages up to the Project-Definition - copy the Project-Topic and the Project-Definition into the Project-Story-Book - take your version of sigmaGuide and
and send it with the subject: TUM Green-Belt-Certification to:
reiner.hutwelker@sigmaLogic.de
10. We will check the suitability of your Project-Definition.
11. If your project is suitable for Six Sigma, then you are automatically registered and we will send you the access data to our TUM EEC learning platform Moodle. There you will find: - the course calendar - the upload/ download area for you documents and our written feedback - your workspace for our one-to-one online coaching - our workspace for online meetings for the entire group
Coaching (Standard- & Business-Projects)
Coaching (Business-Projects) | You will receive written feedback on your Project-Topic and Project-Definition, if necessary with suggestions for changes and feedback on the suitability of your project.
Decision about phase success (Business-Projects) | We will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or we will register you as an participant and welcome you to our course.
Timeline (Example)
Start of Phase | 2020-01-23
Suggested duration (days) | 14
Suggested End of Phase | 2020-02-06
link back to milestones

## GB-Cert-Steps-Define_3
DEFINE (part 3)
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, read handouts, apply sigmaGuide, fill Project-Story-Book template
Deliverables & Checks | sigmaGuide: tool application and approach - SIPOC -> interviews with involved employees & own observations - Voice to Critical -> interview with customer, process owners and experts - Project Charter -> discussion with and approval by Sponsor Project-Story-Book (D): please summarize the important findings of these phase in a comprehensible presentation for your Sponsor. A PowerPoint template for the presentation is available as download in the edx course chapter.
Coaching (Business-Projects) | For our coaching with written feedback, please send your edited versions of sigmaGuide and you Project-Story-Book to: reiner.hutwelker@sigmaLogic.de
You will receive written feedback in your sigmaGuide and Project-Story-Book within a few days.
Additionally one-to-one online coaching's on our learning plattform will be appropriate, if issues of your project need some deeper consideration. We will inform you if this coaching is necessary. To have this coaching, please find a timely appointment in our course calendar.
Coaching (Standard- & Business-Projects) | Open online meetings for the entire group of participants will take weekly, typical at 7:00 UTC and 15:00 UTC on our learning platform. This makes it possible to discuss the main topics of the phase, Q&A´s and to present the projects, if possible. Each participant must during the project overall attend at least 10 open online meetings.
Decision about phase success (Business-Projects) | 1. Master Black Belt (TUM) will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase.
2. Sponsor will finally decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase, based on your presentation of the actual version of the Project-Story-Book.
Timeline (Example)
Start of Phase | 2020-02-07
Suggested duration (days) | 21
Suggested End of Phase | 2020-02-28
link back to milestones

## GB-Cert-Steps-Measure
MEASURE
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, read handouts, apply sigmaGuide, fill Project-Story-Book template
Deliverables & Checks | sigmaGuide: tool application and approach Conduct the 1st workshop with experts of the process and output for the: - Input-Analysis -> 1st workshop with experts - Process-Mapping & -Analysis -> 1st workshop with experts - C&E Matrix -> 1st workshop with experts Please take pictures of the: - participants of the workshop in front of the results of this 1st workshop, - output that demonstrate the problems (as far as possible) and - critical infuences (as far as possible) and append them in your Project-Story-Book - Data Collection Plan -> self-work - Hypothesis -> automatically generated - Data Collection -> measure new data or collect data from existing data bases
Minitab: Worksheet with collected data If you do not have a Minitab license, please download the actual Minitab free trial version at: minitab.com It is recommended, that you use the Windows Version, which is more elaborated than the Mac Version. It is also recommended to first prepare the data in Excel and then to import/paste the data into a Minitab worksheet
Project-Story-Book (DM): please summarize the important findings of these phase in a comprehensible presentation for your Sponsor. A PowerPoint template for the presentation is available as download in the edx course chapter.results edited in Project-Story-Book (DM).
Coaching (Business-Projects) | For our coaching with written feedback, please send your edited versions of sigmaGuide and you Project-Story-Book to: reiner.hutwelker@sigmaLogic.de
You will receive written feedback in your sigmaGuide and Project-Story-Book within a few days.
Additionally one-to-one online coaching's on our learning plattform will be appropriate, if issues of your project need some deeper consideration. We will inform you if this coaching is necessary. To have this coaching, please find a timely appointment in our course calendar.
Coaching (Standard- & Business-Projects) | Open online meetings for the entire group of participants will take weekly, typical at 7:00 UTC and 15:00 UTC on our learning platform. This makes it possible to discuss the main topics of the phase, Q&A´s and to present the projects, if possible. Each participant must during the project overall attend at least 10 open online meetings.
Decision about phase success (Business-Projects) | 1. Master Black Belt (TUM) will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase.
2. Sponsor will finally decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase, based on your presentation of the actual version of the Project-Story-Book.
Timeline (Example)
Start of Phase | 2020-02-29
Suggested duration (days) | 56
Suggested End of Phase | 2020-04-25
link back to milestones

## GB-Cert-Steps-Analyse
ANALYSE
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, read handouts, fill Project-Story-Book template The use of Minitab is explained in the handout: Six-Sigma_Statistics_Minitab
Deliverables & Checks | sigmaGuide: there are no tools for the ANALYSIS phase
Minitab: minimum requirements for inspections and analyses are: - Plausibility Check of collected data (min, max, appropriate scale-level of variables) - Graphically evaluation of collected data (Pareto-Diagram, Time-Series-Plot, Scatter-Plot) - Determination of performance level (sigma-level, DPMO, …) - appropriate Control-Charts (IMR, x-bar/ s, ...) - test of Hypothesis (Chi-squared test, t-test, correlation, regression, ...)
Root Cause Analysis: The root cause analysis is the important link between the ANALYSIS and IMPROVE phase. Conduct the 2nd workshop with experts of the process/ output and conduct the root cause analysis for the problems. The root cause analysis must be displayed as a hierarchy tree and can be developed with a tool of your choice, e.g. with boxes in a PowerPoint slide. Images from a presentation on a flip chart developed in a workshop with experts are also accepted. The presentation as a Fishbone/ Ishikawa cause-and-effect diagram is not accepted. In this 2nd workshop additionally develop solution ideas, which are appropriate to eliminate, adjust or circumvent the root causes. Please take pictures of the: - participants of the workshop in front of the results of this 2nd workshop, - root causes of the problems (as far as possible) and append them in your Project-Story-Book
Project-Story-Book (DMA): please summarize the important findings of these phase in a comprehensible presentation for your Sponsor. A PowerPoint template for the presentation is available as download in the edx course chapter.
Decision about phase success (Business-Projects) | For our coaching with written feedback, please send your edited versions of sigmaGuide and you Project-Story-Book to: reiner.hutwelker@sigmaLogic.de
You will receive written feedback in your sigmaGuide and Project-Story-Book within a few days.
Additionally one-to-one online coaching's on our learning plattform will be appropriate, if issues of your project need some deeper consideration. We will inform you if this coaching is necessary. To have this coaching, please find a timely appointment in our course calendar.
Coaching (Business-Projects) | Open online meetings for the entire group of participants will take weekly, typical at 7:00 UTC and 15:00 UTC on our learning platform. This makes it possible to discuss the main topics of the phase, Q&A´s and to present the projects, if possible. Each participant must during the project overall attend at least 10 open online meetings.
Decision about phase success (Business-Projects) | 1. Master Black Belt (TUM) will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase.
2. Sponsor will finally decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase, based on your presentation of the actual version of the Project-Story-Book.
Timeline (Example)
Start of Phase | 2020-04-26
Suggested duration (days) | 28
Suggested End of Phase | 2020-05-24
link back to milestones

## GB-Cert-Steps-Improve
IMPROVE
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, read handouts, apply sigmaGuide, fill Project-Story-Book template
Deliverables & Checks | sigmaGuide: application of tools and approach - Solution Ideas -> results from 2nd workshop - Action Plan -> Arrangements with the persons responsible for specific action items to implement the solution-ideas - FMEA -> identify and evaluate risks and countermeasures with experts
Project-Story-Book (DMAI): please summarize the important findings of these phase in a comprehensible presentation for your Sponsor. A PowerPoint template for the presentation is available as download in the edx course chapter.
Coaching (Business-Projects) | For our coaching with written feedback, please send your edited versions of sigmaGuide and you Project-Story-Book to: reiner.hutwelker@sigmaLogic.de
You will receive written feedback in your sigmaGuide and Project-Story-Book within a few days.
Additionally one-to-one online coaching's on our learning plattform will be appropriate, if issues of your project need some deeper consideration. We will inform you if this coaching is necessary. To have this coaching, please find a timely appointment in our course calendar.
Coaching (Standard- & Business-Projects) | Open online meetings for the entire group of participants will take weekly, typical at 7:00 UTC and 15:00 UTC on our learning platform. This makes it possible to discuss the main topics of the phase, Q&A´s and to present the projects, if possible. Each participant must during the project overall attend at least 10 open online meetings.
Decision about phase success (Business-Projects) | 1. Master Black Belt (TUM) will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase.
2. Sponsor will finally decide on the success of the project so far and the implementation of solutions, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase, based on your presentation of the actual version of the Project-Story-Book.
Timeline (Example)
Start of Phase | 2020-05-25
Suggested duration (days) | 56
Suggested End of Phase | 2020-07-20
link back to milestones

## GB-Cert-Steps-Control
CONTROL
Course Content | Videos, Handouts, sigmaGuide, Project-Story-Book
Please watch all videos, read handouts, apply sigmaGuide, fill Project-Story-Book template The use of Minitab is explained in the handouts: Six-Sigma-Statistics I & II
Deliverables & Checks | Monitor the implementation of the action-items from the IMPROVE phase accordinmg to the action-list
Collect new data after the implementation of action-items
Minitab: minimum requirements for inspections and analyses are: - plausibility check of collected data (min, max, appropriate scale-level of variables) - graphical evaluation of collected data (Pareto-Diagram, Time-Series-Plot, Scatter-Plot) - calculation of performance level (sigma-level, DPMO, …) - appropriate control-charts (IMR, x-bar/ s, ...) - test of hypothesis (before-after comparison, e.g. with t-test)
sigmaGuide: application of tools and approach - Process-Management-Plan -> Arrangements with the persons responsible for process monitoring and corrective actions - Project-Benefits -> Calculate financial benefits of the improvements and identify other, non-financial benefits
Project-Story-Book (DMAIC): please summarize the important findings of these phase in a comprehensible presentation for your Sponsor. A PowerPoint template for the presentation is available as download in the edx course chapter.
Prerequisite for the Green Belt certification is the: - successful implementation of the project in all DMAIC phases and the - TUM Lean Six Sigma Yellow Belt Certificate
Coaching (Business-Projects) | For our coaching with written feedback, please send your edited versions of sigmaGuide and you Project-Story-Book to: reiner.hutwelker@sigmaLogic.de
You will receive written feedback in your sigmaGuide and Project-Story-Book within a few days.
Additionally one-to-one online coaching's on our learning plattform will be appropriate, if issues of your project need some deeper consideration. We will inform you if this coaching is necessary. To have this coaching, please find a timely appointment in our course calendar.
Coaching (Standard- & Business-Projects) | Open online meetings for the entire group of participants will take weekly, typical at 7:00 UTC and 15:00 UTC on our learning platform. This makes it possible to discuss the main topics of the phase, Q&A´s and to present the projects, if possible. Each participant must during the project overall attend at least 10 open online meetings.
Decision about phase success (Business-Projects) | 1. Master Black Belt (TUM) will check the deliverables and decide on the success of the project so far, either to require adjustments in the current phase or to recommend the transition to the next DMAIC phase.
2. Sponsor will finally decide on the success of the project so far, either to require adjustments in the current phase or to recommend the completion of the DMAIC phases, based on your presentation of the actual version of the Project-Story-Book.
Timeline (Example)
Start of Phase | 2020-07-21
Suggested duration (days) | 14
Suggested End of Phase | 2020-08-04
link back to milestones